## Slide 1
Dr Sipho Kabane
21 April 2016
IDEAL CLINIC SCALE UP PLAN 2016/17

## Slide 2: Contents
Facility Scale-up for 2016/7
Status Determinations
Peer Reviews
Dashboard Versions
Funding Issues
Priorities for 2016/7

## Slide 3
Facilities to be scaled up for 2016/17
1 000 facilities must be identified for scaling up in 2016/17
All NHI facilities to be Ideal by 31 March 2017
Facilities that obtained an Ideal Clinic status during peer reviews process excluded from the 1 000 facilities

## Slide 4
Province | Total Number of PHC Facilities | Facilities in NHI Districts | Number of Ideal Clinics already established | Number of non-NHI facilities to choose from
Eastern Cape | 771 | 145 | 13 | 613
Free State | 221 | 73 | 20 | 128
Gauteng | 365 | 72 | 83 | 210
KwaZulu-Natal | 600 | 130 | 141 | 329
Limpopo | 477 | 124 | 26 | 327
Mpumalanga | 288 | 77 | 19 | 192
North West | 314 | 40 | 7 | 267
Northern Cape | 163 | 36 | 3 | 124
Western Cape | 339 | 48 | - | 291
Total | 3,538 | 745 | 312 | 2,481
Distribution of PHC facilities in provinces

## Slide 5
Provinces to identify facilities
3 538 is the total number of clinics in RSA
Less the 745 NHI already in 2016/7 cohort
Less the 312 clinics that are Ideal
The pool from which the provinces should select their 2016/7 cohort is therefore (2 481)
Target is a 1000 as per APP but more if possible

## Slide 6
Status determinations2016/17
All facilities to have a baseline status determination by 15th of May 2016
They should be conducted by the PPTICRMS
Only by Facility Managers if not feasible
Cohort for 2016/7 will be completed after the 15/05

## Slide 7: Peer Reviews 2016/7
1st Review : September 2016 (500 facilities)
2nd Review: January/ February 2017 (500 facilities)
Reviews will be across districts in the same province

## Slide 8
Ideal Clinic dashboard versions
One version to be implemented/financial year
Version 15 for peer reviews were aligned with version 15 used in 2015/16
Version 16 are in the process to be finalised for implementation 1 April 2016 to 31 March 2017
Version 17 for 2017/18 financial year - will incorporate National Core Standards

## Slide 9: Version 16 (2016/7)
IDEAL CLINIC CATEGORIES (Version 16) |  |  |  |  | 
No of Elements | Weights | Silver | Gold | Platinum | Diamond
15 | Vital | 100% | 100% | 100% | 100%
87 | Essential | 70% | 80% | 91% | 100%
81 | Important | 65% | 75% | 86% | 100%
183 |  |  |  |  | 

## Slide 10
Introduction of Ideal Clinic Component as part of National
Health Insurance Indirect Grant (R10m allocated for 2016/7)
The component is aimed at enabling health sector to address
the deficiencies in the PHC facilities systematically to yield big
fast results.
The grant will fund (outputs) the following @ NHI pilot sites:
  completion, design layout printing and distribution of IC Manual
  740 clinics peer reviewed
  move 740 clinics from average compliance score of 60% to 70%.
Funding: Ideal Clinic Grant

## Slide 11
Business Plan Activities

## Slide 12
Provincial health departments must provide DoH with full and
unrestricted access to all records and data related to the
programme
Provinces must submit provincial needs as per prescribed
format by DoH
Include the ideal clinic indicators in the provincial Annual
Performance Plans (APP)
Delegate a person responsible for managing the Ideal Clinic
programme
Provinces must develop draft implementation plans for taking
over this function in 2019/20
Submit monthly performance reports to DoH
Provincial Responsibilities: IC Grant

## Slide 13
National Health Insurance grant allocation per province is R7.5m.
Managers to ensure effective monitoring of NHI activities as per Business
Plan.
National together with Provincial ICRM coordinators to be part of NHI
monthly meetings and quarterly reviews .
NHI grant ceases to exist this financial year and therefore Business Plans
should be amended immediately for any slow moving activities as funds
will not be rolled over.
When BPs are amended, focus should be on Ideal Clinic. National will
ensure speedy process for BP amendment
FUNDING: NHI Direct Grant

## Slide 14: PRIORITIES FOR 2016/7
Personnel: Appointment of Facility Managers, WISN and Persal Clean-up
Essential Equipment: Emergency trolleys, Delivery packs ,Examination and Resuscitation Equipment
Vitals: O₂, H₂O supply, tracer medicines, Fridges, Air conditioners and thermometers
Infrastructure: Ramps and Rails, Signage
SOP’s; Policies and Guidelines

## Slide 15: The End!!!!!
Thank You!!!!
The End!!!